## Kidtek 2017
Kidtek Marketing Timeline
MEDIA | LEAD/CONTACT | JAN |  |  |  | FEB |  |  |  | MAR |  |  |  | APR | [5 empty] | MAY |  |  |  | JUN |  |  |  | JUL |  |  |  |  | Net Cost | Artwork
Sunday week start |  | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | SF | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30
PLANNING
Class lists developed | Kelly | [32 empty] | Notes | bar: JAN 15 to FEB 5
Spring Break
Classes finalized | Kelly | [32 empty] | Kidtek classes | bar: FEB 19
Marketing plan developed | Jeff | [32 empty] | STEMFEST | bar: FEB 5 to FEB 12
Scholarship details finalized | Kelly & committee | bar: FEB 26
Options Catalog release | CBIZ/MKTG | [18 empty] | ?? | bar: JAN 8
Kidtek classes in session
CATALOG
Final class list delivered to mktg | Kelly | bar: FEB 19
Class descriptions written & returned | Mktg | bar: FEB 19
Class descriptions proofed & approved | Kelly | bar: FEB 26 to MAR 5
Catalog first draft to CBIZ | Mktg | bar: FEB 26
Catalog corrections to mktg | Kelly | bar: FEB 26
Catalog second draft to CBIZ | Mktg | bar: FEB 26
Catalog finished & prepped for print | Mktg | bar: MAR 5
Catalog delivered to printer | Mktg | bar: MAR 5
Catalog distributed to schools | Kelly | [16 empty] | ?? | bar: APR 16
4000
PRINT PROMO - FLYER & POSTER
Save the Date STEM/Kidtek to Kelly | Kelly & Kim | bar: FEB 19
Save the Date STEM/Kidtek to Kim | Kelly & Kim | bar: FEB 26
Save the Date to PRINTER | Kelly & Kim | bar: FEB 26
Save the Date delivered | Kelly & Beth | bar: APR 16
500 | bar: MAR 5
RADIO
STEMFEST | Jeff (radio trade?) | [31 empty] | 500 | bar: APR 9 to APR 16
Kidtek radio promo | Jeff (radio trade?) | [31 empty] | 1500 | bar: APR 16
Kidtek - register now! | Jeff
Kidtek - what are your kids doing? | Jeff
WEBSITE
Online shopping cart testing | Beth & Don | bar: FEB 19 to MAR 5
input classes | Beth & Don | bar: APR 2 to APR 16
update content | Jeff & Beth | bar: FEB 26; APR 2 to APR 16
website live (content, links, etc) | bar: MAR 5
how to register online video | Beth | bar: MAR 19
post link on home page carousel | Jeff | bar: MAR 19
EMAIL PROMO
Generate contact lists | Jeff, Kelly, Beth, Leanne | bar: APR 2
STEMFEST CC 1 | Mktg | bar: APR 9
STEMFEST CC 2 this weekend! | Mktg
Kidtek CC 1 (schols, classes) | Mktg | [32 empty] | ..\communications pieces\Kidtek\kidtek 3 - what are you doing this summer (1).jpg
Kidtek CC 3 reg is now open! | Mktg
Kidtek CC 3 what's your kid doing? | Mktg
Kidtek CC 4 - classes are filling! | Mktg | [31 empty] | 0
Kidtek CC 5 - summer is here! Now what? | Mktg | [31 empty] | 0
Kidtek CC 6 - kids bored? | Mktg
SOCIAL MEDIA PROMO
STEMFEST ads | Mktg | [31 empty] | 50 | bar: APR 16
STEMFEST organic posts | Mktg | [31 empty] | 0 | bar: APR 16
Kidtek organic - scholarships | Mktg | [31 empty] | 0
Kidtek ads - registration/scholarships | Mktg | [31 empty] | 50
Kidtek ads - classes are filling! | Mktg | [31 empty] | 50
Kidtek organic - target class promos | Mktg | [31 empty] | 0
Kidtek ads - still spots left | Mktg | [31 empty] | 50
Kidtek ads - kids bored? | Mktg | [31 empty] | 50
EARNED MEDIA/EDITORIAL
STEMFEST press release | Jeff | bar: APR 9
Kidtek press release | Jeff | [17 empty] | ??
Kidtek reminder to media | Jeff
Kidtek promo for Vision? | Jeff
NON-TRADITIONAL
STEMFEST - KIDTEK booth finalized
STEMFEST yard signs in-hand | Kristine | bar: MAR 26
STEMFEST yard signs posted | STEMFEST cmte | bar: APR 16
Kidtek/STEMFEST signs swapped | Kelly/Beth?
Kidtek signs picked up | Kelly/Beth?
WB & Keo marquees - STEMFEST | Jeff | bar: APR 16
WB & Keo marquees - Kidtek | Jeff
Finalize t-shirt artwork | Jeff
Order tees | Kelly/Beth?
Tees delivered | Kelly/Beth?
TOTAL | [32 empty] | 6750